## Sheet1
Smart Alarm Clock
Royal University of Phnom Penh |  | Faculty of Engineering
Deadline: 4/30/2023
Action | Responsible | Start Date | End Date
Week #1: Researching
ESP32 Module | Sreynen | 2023-02-20 | 2023-02-22
Thunkable + Text to speech | Soriya | 2023-02-20 | 2023-02-24
7 segment 4 digit ft speaker | Sreynen | 2023-02-23 | 2023-02-25
Discussing | Group | 2023-02-20 | 2023-02-26
Week #2&3: Hardware
ESP32 Module ft 7 segment | Soriya | 2/28/2023 | 2023-03-14
ESP32 Module ft speaker | Sreynen | 2/28/2023 | 2023-03-14
Discussing | Group | 2023-02-28 | 2023-03-14
Week #4&5: Software
Thunkable + Text to speech | Soriya | 2023-03-17 | 2023-03-31
ARDUINO IDE | Sreynen | 2023-03-17 | 2023-03-31
Discussing | Group | 2023-03-17 | 2023-03-31
Week #6&7: Software and Hardware testing
ARDUINO IDE |  | 2023-04-01 | 2023-04-07
Thunkable + Text to speech |  | 2023-04-01 | 2023-04-07
ESP32 Module |  | 2023-04-08 | 2023-04-13
ESP32 Module ft 7 segment |  | 2023-04-08 | 2023-04-13
7 segment 4 digit ft speaker |  | 2023-04-13 | 2023-04-13
Discussing | Group | 2023-04-01 | 2023-04-13
Week #8: Retesting and Circuit Design
Retesting |  | 2023-04-15 | 2023-04-22
Circuit Design |  | 2023-04-15 | 2023-04-22
Discussing | Group | 2023-04-15 | 2023-04-22
Week #9 3D Print
3D Print |  | 2023-04-23 | 2023-04-30
Discussing | Group | 2023-04-23 | 2023-04-30